## Sheet1
ITEMS | Description | Module | Dependencies and Tasks | Query and Understanding | Estimate in Hours | Status
1 | Page B on app front end - After choose address | Residential sales tracking process in app (from route to market to outcome tracking process) | App: 1: Suburb screen design changes and implement dropdown for streets/sites. Backend : 1: Save, suburb as per selected category API. 2: Get streets worked, site worked as per selected category API. 3: Save house number or business name and person API. 4: Need modification in sales step screen API 5: Save sales step API modification 6: DB Schema modification(Tables for storing suburb and sub items) 7: Existing table structure modification for sales tracking to suburb Other Implacted Areas: 8: Report module modification in admin due to db schema change 9: Data overview module modification in admin due to db schema change 10: Dashboard Top users and top companies modification in admin due to db schema change 11: Data matrix modification API modification 12: My teams API modications |  | Backend: (as all three of them has the same flow with few changes) Point 1-7 (Dependencies and tasks): 10 Hours Point 8-12(Dependencies and tasks): 22 Hours APP : 12 hours
2 |  | B2B sales tracking process in app(from route to market to outcome tracking process)
3 |  | Events sales tracking process in app(from route to market to outcome tracking process)
4 | History table underneath page B | Outcome TRACKING - History | When the user enters the data into the data collection, the details are entered into the table below. The VIEW + triggers the popup so that the user can view what data they have entered, and can change it if needed. The headers in the rows are as follows: ID (simple ID increments so that each entry has a unique number) DATE (this is automatic - can be sorted in order by clicking ascending / descending toggle) Outcome (the name of the step that they pressed on) Count VIEW + When the user presses on the + there is a modal popup so that the data entry can be viewed. This is for error checking or if the user needs to change something. | We have a query here. On what basis will the outcome history be displayed. Will it be based on route to market type, or suburb, or the combination of both? Also, does that mean that as soon as the user enters the variables, the outcome history will be reflected automatically. ANSWER: I don't think anything needs to be recorded until the user presses the appropriate button on the data collection page My Comment: Understood, the estimate remains same | Back-end = 8 hours APP= 8 hours
5 | Front end data collection | OUTCOME TRACKING - Data Collection | Residential, B2B & Events The ADD CALLBACK button and NQ button at the bottom, also EXISTING CUSTOMER |  | Back-end = 8 hours NQ API, View metrics and report changes =NQ count, suburb panel, design modifications, Report PDF changes APP: 6 hours EC= 8 hours (4+4= app and backend)
6 | Information gets refreshed at end of everyday | Add a logout fallback so that at 12am everyday all users are logged out and revert all daily numbers to revert back to zero (0) | Keep historical data Reset daily data to 0 Sales step count |  | Backend: 8 Hours APP: 2 hours
7 | Callbacks get refreshed at the end of every 8 days | 1. Callbacks to be collected and removed every 8 days 2. Will design and implement new callback screen with filters 'show today'and ''active. | Backend : 1:Cron job implementation for removing old callbacks 2: Modify callbacks api for getting filterred data as per applied filter. 3: Modification in admin module and table for storing priority and status. App: 1: Callback screen design changes. 2: Api changes implementation and filters changes in app | How to identify the status of callbacks? Who will maintain the status? Front-end user or back-end user? Because as of now we are only displaying the callbacks listing only that is coming from the back-end. So by default as soon as the call back sets, it remains active. So how to define its active and inactive state? ANSWER: Status of callback is always defined by the front end user. The status changes on the press of the action button. The status changes from the X to the O. By default the callback needs to be set at ACTIVE (the O) and when pressed the status changes to ACTIONED (the X) My Comment: Understood, the estimate remains same | Backend: 8 Hours APP: 8 hours
8 | Additional user account | Original User accounts: Master Admin - dashboard Company Manager - dashboard / app / view all users on company Overview Manager - app / view team User - app only Updated User account: Overview Manager + Admin: Same as original overview, but also has limited admin access to the user setup, team setup (with no access to company setup or sales step setup) | When they click on the MY TEAM on the app, they can only see their team metrics. Also, you mean while company is creating overview managers, there should be an option (checkbox sort of) to allow this manager to have admin access. If checked then user will be able to access all the functionality that a master is having BUT with VIEW only permission/access. Please confirm. |  | Backend: 16 Hours APP: 2 hours
9 | Master admin (you) have ability to change the status of the company dependant on what they wish to do - all data is retained online until they want to reactivate it all again | Managing Statuses | STATUS: Active - current Suspended – Haven't paid Bill – have 0 access On Hold – No user access, only the directors and admin users can access data on online portal (this is for times when their team can't work) Grace Period(1 yr after termination) – we maintain their historical data, the company settings and User details for a year to make it easier for them to restart Email gets MA: Can the Statuses of Company be: sent out asking if they want to activate their account again CRON JOB: - 14 days - if no action has been taken, change status to INACTIVE and change password. - Email gets sent out stating the OT account has been terminated, if they wish to reactivate it, they have to contact admin for reactivation. - Inactive (after 1st yr) – they have to start again - Timer on INACTIVE STATUS, after 365 days it gets removed. | We haven't heard on this point yet so we are not implemeting this one in this CR ANSWER: I am not sure what you need to know extra than what you have already said here. This is correct what you have suggested. Once status has been changed, this triggers an email that informs the company manager about the status of the account. The email will need to have a trigger button on it, so that they can confirm. Once pressed the account goes into the status conditions and the button triggers the condition. If the button isn't pressed within 14days, the account is removed. My Comment: Understood. | 6 hours
LEAVE THIS ONE | STAGE 2 - not needed at launch | Trial account for app users - Default company will be OUTCOMES TRACKING - Email gets sent out automatically with conditions and welcome - Trial accounts will add a new user to the default company - Trail users are active for 7 days and have all normal user access - After 7 days notice gets triggered about activation (nurture sequence) - Trial only allows 25 interactions | I would want just my set sales steps to be the sales step for a trial account. All different routes to market need to be available, and they would just use the pages A, B & outcomes tracking just as a normal user would. I would give them the ability to enter in 25 interactions, max. Once 25 interactions are logger can they get a pop up to say “that is the max interactions allowed for the trial account”. There would need to be some example “callbacks” There would be just a set example of historical data so they can see how it is presented.There would just be a set example of visibility over team stats. That’s all I can think of that would be different from a normal account. And I ' m not thinking the “trial” comes with access to a trial online portal, just the app. And what's your thoughts? We create a trial account login and then just change the password monthly so that competitors if they do get access to the trial account, wont have continual access to it? | We are assuming that the team or users will be created by the company admin only. So what we will do is that we will create a trial role as well as a trial team. We will add all triall users to trial team. Setup the cron job to reset password after 30 days or daily basis. In the back-end we will sort of create a new role wherein we will set validations. Also it would be hard-coded i.e. 25 interactions. If it should be customized then it would be cost accordingly. Also, since we need to show the trial data to the normal app users in the reports, metrics, and PDF therefore we have to apply a filter not to show the trial data in the actual PDFs.We can update/change the password either on a daily basis or can be updated monthly-wise for those users. Please confirm the same and if there is any chnage in the understanding, let me know. | Back-end: 24 hours
11 | Team Manager table | Team Manager changes | Team Manager: Please make the team manager section as per our conversation and as per this screenshot. Make the ROLE values colour coded Overview Manager is always at position 1 Ability for users to be in multiple teams Add in new column to show ADMIN ACCESS (yes / no) Ability to sort in alphabetical order on click of header rows | What we have implemented after our discussion is that where you have mentioned multiple companies, we have shown the listing of teams and under this as a child we will show all the team members like below: So it won’t be similar to the one you have pasted here. On this I have already updated that it shouldn't be exactly your screenshot attached.Your screenshot has multiple companies. How come there can be multiple companies when there should be only 1 company that creates team. So where you have mentioned company details in the screenshot at the bottom, we will display list of teams instead. Please confirm our understanding. If this correct then there is no extra cost. But there is any changes in this it will estimated accordingly. ANSWER: The team manager that the MASTER ADMIN sees needs multiple companies. The master admin doesn't need to change anything, just a visual. They need to see extra columns in the current setup as it has to show the TEAM NAME / NUMBER and also the colour coded positions. My Comment: Understood, the estimate remains same | Back-end: 8 hours
|  |  | Total Hours |  | 140
|  |  | Total Man Weeks |  | 3.5 Weeks
|  |  | Total Cost for items 1,2,3,4 |  | $1,950 + GST
|  |  | Total cost after Discount on items 1,2,3,4 |  | $1,755 + GST
|  |  | Total Cost for items 5,6,7,8,9,11 |  | $2,600 + GST
|  |  | Total Cost for items 1,2,3,4,5,6,7,8,9,11 |  | $4,550 + GST
|  |  | Total Cost for all the items(1 to 11-except 10) affter Discount on items 1,2,3,4 |  | $4,355 + GST