## v1.2
Project : Treeboard (15613) v.1.0 - Sprint Planning
Sprint 1 ( Design and HTML Development/Adjustment ) | S.NO | Module | Week | Developer 1
Design
| 1 | Logo Desing | 1 | ✔
| 2 | Home page | 1 | ✔
| 3 | Subscription Plan | 1 | ✔
|  | HTML (ATS) | 1 | ✔
| 4 | Home page | 1 | ✔
| 5 | Subscription Plan | 2 | ✔
| 6 | Dashboard | 2 | ✔
|  | Create/Post Jobs | 2 | ✔
|  | -Enter Job Details | 2 | ✔
|  | -Create Schedule | 2 | ✔
|  | #NAME? | 2 | ✔
|  | -View Details | 2 | ✔
|  | -Select plateforms | 2 | ✔
|  | -Reviews Job posts | 2 | ✔
| 7 | Manage Interviews | 2 | ✔
| 8 | Hiring Dashboard | 2 | ✔
| 9 | Job Application listing/Details and Search page | 2 | ✔
| 10 | View Applicant Details | 2 | ✔
| 11 | Add/Edit Staff Members | 2 | ✔
| 12 | Register(Sign up) | 2 | ✔
| 13 | Sign in | 2 | ✔
| 14 | Payment/Checkout Page | 2 | ✔
| 15 | Create Profile (Add Organisation details) | 3 | ✔
| 16 | Notifications | 3 | ✔
| 17 | Content Pages:- | 3 | ✔
|  | -About Us | 3 | ✔
|  | -Contact Us | 3 | ✔
|  | -Terms & condition | 3 | ✔
|  | -Privacy Policy | 3 | ✔
|  | -FAQ’s | 3 | ✔
|  | -Help & Support | 3 | ✔
|  | -Career Pages | 3 | ✔
| 18 | Template Management | 3 | ✔
| 19 | Settings | 3 | ✔
| 20 | Bug Fixing | 3 | ✔
|  | QA Release Date (Sprint 1) | 28th October 2021
|  | Client Release Date (Sprint 1) | 29th October 2021
Sprint 2 (Super Admin and Front-End) |  | Super Admin panel
| 21 | Sprint 1 Feedback
| 22 | Login/Forgot password/Rest Password | 3 | ✔
| 23 | Dashboard Panel | 3 | ✔
| 24 | Manage Company/Recruiter | 3 | ✔
| 25 | Admin Settings | 3 | ✔
| 26 | Account Settings | 4 | ✔
| 27 | Manage Email Templates | 4 | ✔ | Bug Fixing
| 28 | Manage Content page | 4 | ✔
| 29 | Manage Contact enquries | 4 | ✔
| 30 | Manage Notification | 4
| 31 | Bug Fixing | 4 | ✔
|  | QA Release Date (Sprint 2) | 09th November 2021
|  | Client Release Date (Sprint 2) | 11th November 2021
|  | Front-End | 5 | ✔
| 32 | Sprint 2 Feedbacks | 5 | ✔
| 33 | Home page | 5 | ✔
Sprint 3 (Front- End) | 34 | Subscription Plan | 5 | ✔
| 35 | Dashboard | 5 | ✔
| 36 | Register(Sign up) | 5 | ✔
| 37 | Sign in | 5 | ✔
| 38 | Forgot Password | 6 | ✔
| 39 | Create Profile (Add Organisation details) | 6 | ✔
|  | Content Pages:- | 6 | ✔
|  | -About Us | 6 | ✔
|  | -Contact Us | 6 | ✔
|  | -Terms & condition | 6 | ✔
|  | -Privacy Policy | 7 | ✔
|  | -FAQ’s | 7 | ✔
|  | -Help & Support | 7 | ✔
|  | -Career Pages | 7 | ✔
| 40 | Settings | 7 | ✔
| 41 | Bug Fixing | 7 | ✔
|  | QA Release Date (Sprint 3) | 22th November 2021
|  | Client Release Date (Sprint 3) | 24th November 2021
Sprint 4 ( Super Admin Panel - Front- End ) |  | Super Admin panel
| 42 | Sprint 3 Feedbacks | 7 | ✔
| 43 | Reporting Manager | 7 | ✔
| 44 | Manage Subscriptions | 7 | ✔
| 45 | Payment Management | 7 | ✔
| 46 | Third-Party Job Feeds Integration | 7 | ✔
Front-end
| 47 | Create/Post Jobs | 8 | ✔
|  | -Enter Job Details | 8 | ✔
|  | -Create Schedule | 8 | ✔
|  | -Compensation | 8 | ✔
|  | -View Details | 8 | ✔
|  | -Select plateforms | 8 | ✔
|  | -Reviews Job posts | 9 | ✔
| 48 | Job Application listing/Details and Search page | 9 | ✔
| 49 | Payment Gateway | 9 | ✔
| 50 | Payment/Checkout Page | 10 | ✔
| 51 | Template Management | 10 | ✔
Sprint 5 | 52 | Bug Fixing | 10 | ✔
|  | QA Release Date (Sprint 4) | 06th December 2021
|  | Client Release Date (Sprint 4) | 08th December 2021
| 53 | Sprint 4 Feedbacks | 10 | ✔
| 54 | View Applicant Details | 11 | ✔
| 55 | Manage Interviews | 11 | ✔
| 56 | Hiring Dashboard | 12 | ✔
| 57 | Add Staff Members | 12 | ✔
| 58 | Notifications | 12 | ✔
| 59 | Bug Fixing | 12 | ✔
|  | QA Release Date (Sprint 4) | Yet to Finalize
|  | Client Release Date (Sprint 4) | Yet to Finalize (must be in the first week of Jan 20222)