## G2B2-212
[9 empty] | Test Run #1 |  |  |  |  | Test Run #2 |  |  |  |  | Test Run #3 |  |  |  |  | Test Run #4 |  |  |  |  | Test Run #4
CR NO. | Create Date | Module\CR Description | Test Case Id | Testing Type | Description | Execution steps | Test Data | Expected Result | Execution Date | Actual Result | Test Data | Result | Defect Id | Execution Date | Actual Result | Test Data | Result | Defect Id | Execution Date | Actual Result | Test Data | Result | Defect Id | Execution Date | Actual Result | Test Data | Result | Defect Id | Execution Date | Actual Result | Test Data | Result | Defect Id
G2B2-212 | 26/11/2018 | New Confirmation Statement GDPR and PTR | TC_01 | Functional | Verify G2B Quote is added/edited or not for OF/OC brand. | 1. Login CRM as management/agent. 2. Go to enquiry view. 3. Add/edit G2B Quote. | NA | A G2B Quote should be add/edit for OF/OC brand. | 27/11/2018 | G2B Quote is adding/editing for OF/OC brand. | OH494665 OH494666 | PASS
G2B2-212 | 26/11/2018 | New Confirmation Statement GDPR and PTR | TC_02 | Functional | Verify email is sent or not for OF/OC lead when click on the 'Send to Confirm to Confirm' button. | 1. Login CRM as management/agent. 2. Go to enquiry view. 3. Add/edit G2B Quote. 4. Add single/multiple products detail. 5. Click on the 'Send to Confirm to Confirm' button. | NA | OF/OC lead Email should be successfully sent to the client given email when click on the 'Send to Confirm to Confirm' button. | 27/11/2018 | Email is sent for OF/OC lead when click on the 'Send to Confirm to Confirm' button. | OH494665 OH494666 | PASS
G2B2-212 | 26/11/2018 | New Confirmation Statement GDPR and PTR | TC_03 | Functional | Verify IF a single product added in the G2B quote for OF/OC lead then according to the attached document in the card, details is appear or not in underneath of the 'PRICING AND PAYMENT' section details on the below pages: Preview Client's Email Confirmation Email View G2BQuote Outro Committed Booking Sent Email Quote Outro (Confirm Now and Pay) Confirmed Booking Sent Email TD Complete Agent Outro | 1. Login CRM as management/agent. 2. Go to enquiry view. 3. Add/edit G2B Quote. 4. Add single product detail. 5. Click on the 'Send to Confirm to Confirm' button. 6. Verify details on Preview Client's Email/ Confirmation Email View/G2BQuote Outro Committed Booking Sent Email/Quote Outro (Confirm Now and Pay)/Confirmed Booking Sent Email/TD Complete Agent Outro | NA | IF a single product added in the G2B quote for OF/OC lead then according to the attached document in the card, details should appear in 'ADDITIONAL INFORMATION' section on the below pages: Preview Client's Email Confirmation Email View G2BQuote Outro Committed Booking Sent Email Quote Outro (Confirm Now and Pay) Confirmed Booking Sent Email TD Complete Agent Outro | 27/11/2018 | Details appear in underneath of the 'PRICING AND PAYMENT' section on the below pages if a single product added in the G2B quote for OF/OC lead then according to the attached document in the card: Preview Client's Email Committed Booking Sent Email Confirmation Email View G2BQuote Outro Quote Outro (Confirm Now and Pay) Confirmed Booking Sent Email TD Complete Agent Outro. | OH494665 OH494666 | PASS
G2B2-212 | 26/11/2018 | New Confirmation Statement GDPR and PTR | TC_04 | Functional | Verify that according to OF/OC brand specific lead, Privacy policy text link is appear or not underneath of the 'PRICING AND PAYMENT' section details. On clicking that text link, the page is navigate or not to browser page in next tab. | 1. Login CRM as management/agent. 2. Go to enquiry view. 3. Add/edit G2B Quote. 4. Add single product detail. 5. Click on the 'Send to Confirm to Confirm' button. 6. Verify details on Preview Client's Email/ Confirmation Email View/G2BQuote Outro Committed Booking Sent Email/Quote Outro (Confirm Now and Pay)/Confirmed Booking Sent Email/TD Complete Agent Outro. 7. Click on 'T&C' text link. | NA | According to OF/OC brand specific lead, Privacy policy text link should appear underneath of the 'Additional Information' details. On clicking that text link, the page should navigate to browser page in next tab. | 27/11/2018 | According to OF/OC brand lead, Privacy policy text link appears underneath of the 'PRICING AND PAYMENT' section details. When clicking that text link, the page is navigated to browser page in next tab. | OH494665 OH494666 | PASS
G2B2-212 | 26/11/2018 | New Confirmation Statement GDPR and PTR | TC_05 | Functional | Verify IF Multiple products added in the G2B quote for OF/OC lead then according to the attached document in the card, details is appear or not underneath of the 'PRICING AND PAYMENT' section details on the below pages: Preview Client's Email Confirmation Email View G2BQuote Outro Committed Booking Sent Email Quote Outro (Confirm Now and Pay) Confirmed Booking Sent Email TD Complete Agent Outro | 1. Login CRM as management/agent. 2. Go to enquiry view. 3. Add/edit G2B Quote. 4. Add single product detail. 5. Click on the 'Send to Confirm to Confirm' button. 6. Verify details on Preview Client's Email/ Confirmation Email View/G2BQuote Outro Committed Booking Sent Email/Quote Outro (Confirm Now and Pay)/Confirmed Booking Sent Email/TD Complete Agent Outro | NA | IF Multiple products added in the G2B quote for OF/OC lead then according to the attached document in the card, details should appear in 'ADDITIONAL INFORMATION' section on the below pages: Preview Client's Email Confirmation Email View G2BQuote Outro Committed Booking Sent Email Quote Outro (Confirm Now and Pay) Confirmed Booking Sent Email TD Complete Agent Outro | 27/11/2018 | Details appear in underneath of the 'PRICING AND PAYMENT' section on the below pages if multiple products added in the G2B quote for OF/OC lead then according to the attached document in the card: Preview Client's Email Committed Booking Sent Email Confirmation Email View G2BQuote Outro Quote Outro (Confirm Now and Pay) Confirmed Booking Sent Email TD Complete Agent Outro. | OH494665 OH494666 | PASS
G2B2-212 | 26/11/2018 | New Confirmation Statement GDPR and PTR | TC_06 | Functional | Verify that according to OF/OC brand lead, Terms & Conditions text link is appear or not underneath of the 'PRICING AND PAYMENT' section details. On clicking that text link, the page is navigate or not to browser page in next tab. | 1. Login CRM as management/agent. 2. Go to enquiry view. 3. Add/edit G2B Quote. 4. Add single product detail. 5. Click on the 'Send to Confirm to Confirm' button. 6. Verify details on Preview Client's Email/ Confirmation Email View/G2BQuote Outro Committed Booking Sent Email/Quote Outro (Confirm Now and Pay)/Confirmed Booking Sent Email/TD Complete Agent Outro. 7. Click on 'T&C' text link. | NA | According to OF/OC brand lead, Terms & Conditions text link should appear underneath of the 'Additional Information' details. On clicking that text link, the page should navigate to browser page in next tab. | 27/11/2018 | According to OF/OC brand lead, Terms & Conditions text link appears underneath of the 'PRICING AND PAYMENT' section details. On clicking that text link, the page is navigated to browser page in next tab. | OH494665 OH494666 | PASS
Reporting - Trade Client Ref Update